ELT PCS R&D Study

WP 3.4: Polarimetry

Management Plan

| Version | 0.1 |
| --- | --- |
| Date | May 2026 |
| Lead | Daniel Smith — polarimetry lead |
| Status | Draft |

1. WP3.4 Overview

| Leads | 1. Daniel Smith — polarimetry lead for PCS 2. To be filled |
| --- | --- |
| Start / End | Start: June 2026 End: ~June 2028 |

| Objectives | Develop and evaluate polarimetry implementation concepts for PCS, covering imaging polarimetry and spectropolarimetry at low and high spectral resolution across visible and near-infrared wavelengths. |
| --- | --- |
|  | • Conduct an inventory and benchmarking of previous instruments that implemented polarimetry (SPHERE, GPI, SCExAO, CHARIS, Roman CGI, CRIRES+, ZIMPOL) to extract best practices and lessons learned. |
|  | • Identify design drivers for polarization in the context of PCS. |
|  | • Develop an Exposure Time Calculator (ETC) for polarimetry to feed into WP7 science yield calculations. |
|  | • Model ELT telescope-induced polarization systematics and assess the impact of the K-mirror on the polarimetric design (waveplate placement before or after K-mirror; multiple quarter-wave plates for compensation). |
|  | • Assess feasibility of achromatic waveplate designs and bandwidth limitations. |
|  | • Evaluate modulation architectures (dual beam vs temporal modulation). |
|  | • Translate science requirements into technical requirements for polarimetry. |
|  | • Develop optical design recommendations based on best practices for polarisation-safe designs. |
|  | • Monitor PCS optical design development and flag polarisation-incompatible choices. |

| Inputs | • TLRs (Top-Level Requirements) from WP1: wavelength range, field of view, spatial sampling, polarimetry requirements. |
| --- | --- |
|  | • WP3 overall instrument concept documents. |
|  | • Interface document and error budget from WP6 (System Concept). |
| Outputs | 1. Instrument benchmarking report. |
|  | 2. Polarimetric trade study (imaging vs spectropolarimetry; visible vs IR; low vs high resolution). |
|  | 3. ELT polarisation modelling report. |
|  | 4. Calibration strategy document. |
|  | 5. Polarimetric error budget. |
|  | 6. Optical design rules for polarisation-safe design. |
|  | 7. Architecture recommendation for WP3.4 baseline concept. |
|  | 8. PDR (Preliminary Design Review) package contribution. |
| Deliverables | Year 1 milestones (by end of December 2026): Science case, requirements, baseline architecture, identified risks. |
|  | Preliminary Design Review (by Spring 2028): Full system architecture, performance simulations, risk mitigation plan. |
| Resources | Design tools: Python, IDL, Zemax OpticStudio (polarisation ray tracing). |
|  | General tools: Microsoft Word, Microsoft Excel. |
|  | Communication: Microsoft Teams (ESO PCS SharePoint site), regular monthly meetings. |

2. Boundary Conditions

The following boundary conditions currently govern the WP3.4 polarimetry work:

- No final instrument design exists yet for PCS; all polarimetry concepts must be adaptable to the emerging instrument architecture.

- Three polarimetry modes are under consideration:

- Imaging polarimetry

- Spectropolarimetry at low spectral resolution

- Spectropolarimetry at high spectral resolution

- Science-level polarimetric requirements are not yet clearly defined and will need to be established as part of this work package.

- The polarimetric modulation scheme (dual beam vs temporal, waveplate type and placement) has not yet been decided.

3. Calibration Strategy

Key considerations for the polarimetric calibration strategy:

- Finding suitable infrared polarimetric standard stars may be difficult, which could impose a fundamental accuracy limitation of approximately 1% on infrared polarimetry:

- A realistic calibration floor for the infrared must be established through dedicated study.

- Limitations from variable dust and disk properties around potential calibrators must be assessed.

- For optical/visible wavelengths, the calibration situation is significantly more favourable: there is an ample supply of calibration standards and no expected fundamental limitation at the 1% level.

- A dedicated study is required to obtain a more realistic number for the infrared calibration floor.

- Calibration validation on prototype systems is planned for early 2028 (see Section 6: Schedule).

4. Work Breakdown Structure (WBS)

WP 3.4 is structured into the following activities, grouped into three phases.

Phase 1 — Benchmarking and Requirements (June 2026 – November 2026)

- WP 3.4.1: Instrument Benchmarking — Survey of SPHERE, GPI, SCExAO, CHARIS, Roman CGI, CRIRES+, ZIMPOL to extract best practices and lessons learned for polarimetry implementation.

- WP 3.4.2: Polarimetry Trade Study — Comparative evaluation: imaging vs spectropolarimetry; visible vs infrared; low vs high spectral resolution.

- WP 3.4.3: Science Requirements — Translation of PCS science goals into quantitative technical requirements for polarimetry.

- WP 3.4.4: Polarimetric Sensitivity Study — Determination of sensitivity and contrast requirements for science cases.

Phase 2 — Design Studies (July 2026 – March 2027)

- WP 3.4.5: ELT Polarisation Modelling — Modelling of telescope-induced polarization systematics (M1–M6 mirrors, K-mirror).

- WP 3.4.6: K-Mirror Trade Study — Evaluation of waveplate placement options relative to the K-mirror field derotator; assessment of compensation strategies using multiple quarter-wave plates.

- WP 3.4.7: Waveplate Bandwidth Study — Feasibility and bandwidth limits of (super-)achromatic waveplate designs.

- WP 3.4.8: Modulation Architecture — Evaluation of dual beam versus temporal modulation schemes.

- WP 3.4.9: Calibration Strategy — Establishing the infrared calibration floor, identifying suitable standard stars, assessing variability effects.

- WP 3.4.10: Optical Design Rules — Developing a set of polarisation-safe optical design constraints and recommendations for the PCS optical design.

Phase 3 — Integration and Review (January 2027 – June 2028)

- WP 3.4.11: End-to-End Simulations — Integrated AO + coronagraph + detector + polarimetry performance simulations.

- WP 3.4.12: Polarimetric Error Budget — Quantification of cross-talk, residual systematics, and achievable polarimetric limits.

- WP 3.4.13: Subsystem Prototyping — Waveplate, modulator, and polarimetric stability test bench.

- WP 3.4.14: Detector Trade Study — Evaluation of EMCCD, SAPHIRA, and IR array options for polarimetric science.

- WP 3.4.15: IFU Polarimetry Study — Feasibility of combining integral field unit spectroscopy with polarimetric capability.

- WP 3.4.16: Fiber Injection Study — Feasibility of coupling polarimetry with the high-dispersion spectroscopy (HDS) fibre injection channel.

- WP 3.4.17: Architecture Freeze — Selection of baseline PCS polarimetry architecture.

- WP 3.4.18: PDR Package — Preparation of the Preliminary Design Review contribution for WP3.4.

- WP 3.4.19: Calibration Validation — Validation of calibration strategy on prototype systems.

- WP 3.4.20: Stability Testing — Long-term thermal and polarimetric stability measurements.

- WP 3.4.21: Final Polarimetry Review — Final review and risk assessment.

5. Receivables and Deliverables

Table 1: Receivables for WP3.4

| From | Description | When |
| --- | --- | --- |
| WP1 (Science) | Top-Level Requirements (TLRs) with specific polarimetry requirements. | October 2025 |
| WP2 (Coronagraph + WFS) | Conceptual design document: ADC details, wavefront error estimate. | June 2026 |
| WP6 (System Concept) | Interface document and error budget. | February 2026 |
| WP6 (System Concept) | Response report to instrument concept design V1. | July 2026 |
| WP3 (Instrument Concept) | Overall instrument architecture and constraints from WP3.1–3.3. | Ongoing |

Table 2: Deliverables for WP3.4

| To | Description | When |
| --- | --- | --- |
| WP3 (Instrument Concept) | WP3.4 benchmarking report and trade study. | December 2026 |
| WP6 (System Concept) | Polarimetry contribution to instrument conceptual design V1. | June 2026 |
| WP6 (System Concept) | Polarimetry contribution to instrument final design V2. | April 2027 |
| WP7 (Science Yield) | Polarimetric ETC and sensitivity estimates. | February 2027 |
| All WPs | Optical design rules for polarisation-safe design. | March 2027 |
| All WPs | Polarimetric error budget. | July 2027 |
| All WPs | PDR package contribution. | February 2028 |

6. Schedule

The schedule below reflects the current planning for WP3.4 activities. All tasks overlap partially; the time frame column indicates the planned active period. Tasks without a sign-up are currently open for team members to volunteer.

Table 3: Schedule for WP3.4 Activities

| Task Name | Short Overview | Start | Duration (days) | End | Time Frame |
| --- | --- | --- | --- | --- | --- |
| Instrument Benchmarking | Survey SPHERE, GPI, SCExAO, CHARIS, Roman CGI, CRIRES+, ZIMPOL | 01 Jun 2026 | 90 | 30 Aug 2026 | Jun → Aug 2026 |
| Polarimetry Trade Study | Imaging vs spectropolarimetry; visible vs IR; low vs high R | 15 Jun 2026 | 120 | 13 Oct 2026 | Jun → Oct 2026 |
| Science Requirements | Translate science goals into technical requirements | 01 Jul 2026 | 150 | 28 Nov 2026 | Jul → Nov 2026 |
| Polarimetric Sensitivity Study | Sensitivity and contrast requirements | 01 Aug 2026 | 120 | 29 Nov 2026 | Aug → Nov 2026 |
| ELT Polarisation Modeling | Telescope-induced polarization systematics | 12 Jul 2026 | 180 | 11 Jan 2027 | Jul 2026 → Jan 2027 |
| K-Mirror Trade Study | Waveplate placement and K-mirror compensation | 01 Aug 2026 | 120 | 29 Nov 2026 | Aug → Nov 2026 |
| Waveplate Bandwidth Study | Achromatic waveplate feasibility and bandwidth limits | 15 Aug 2026 | 120 | 13 Dec 2026 | Aug → Dec 2026 |
| Modulation Architecture | Dual beam vs temporal modulation | 01 Sep 2026 | 150 | 29 Jan 2027 | Sep 2026 → Jan 2027 |
| Calibration Strategy | IR calibration floor, standards, variability | 01 Sep 2026 | 180 | 28 Feb 2027 | Sep 2026 → Feb 2027 |
| Optical Design Rules | Polarisation-safe optical design constraints | 01 Oct 2026 | 180 | 30 Mar 2027 | Oct 2026 → Mar 2027 |
| End-to-End Simulations | AO + coronagraph + detector + polarimetry simulation | 01 Jan 2027 | 240 | 29 Aug 2027 | Jan → Aug 2027 |
| Polarimetric Error Budget | Cross-talk, residuals, systematic limits | 01 Feb 2027 | 180 | 31 Jul 2027 | Feb → Jul 2027 |
| Subsystem Prototyping | Waveplate/modulator/stability test bench | 01 Apr 2027 | 240 | 27 Nov 2027 | Apr → Nov 2027 |
| Detector Trade Study | EMCCD vs SAPHIRA vs IR arrays | 01 Mar 2027 | 120 | 29 Jun 2027 | Mar → Jun 2027 |
| IFU Polarimetry Study | Feasibility of IFU spectropolarimetry | 15 Mar 2027 | 150 | 12 Aug 2027 | Mar → Aug 2027 |
| Fiber Injection Study | Coupling polarimetry with HDS fibre injection | 01 Apr 2027 | 120 | 30 Jul 2027 | Apr → Jul 2027 |
| Architecture Freeze | Select baseline PCS polarimetry architecture | 01 Oct 2027 | 45 | 15 Nov 2027 | Oct → Nov 2027 |
| PDR Package | Preliminary design review package | 15 Nov 2027 | 90 | 13 Feb 2028 | Nov 2027 → Feb 2028 |
| Calibration Validation | Validate calibration strategy on prototype systems | 15 Jan 2028 | 90 | 14 Apr 2028 | Jan → Apr 2028 |
| Stability Testing | Long-term thermal and polarization stability | 01 Feb 2028 | 120 | 31 May 2028 | Feb → May 2028 |
| Final Polarimetry Review | Final review and risk assessment | 15 May 2028 | 30 | 14 Jun 2028 | May → Jun 2028 |

7. Instrument Benchmarking — Trade Study

This section presents a comparative study of existing high-contrast polarimetric instruments. Two tables are provided: Table 4 draws on information collated from the PCS Teams SharePoint documents; Table 5 incorporates additional information from the published literature and public instrument documentation. The goal is to inform the polarimetric design of PCS through lessons learned from heritage instruments.

Table 4: Instrument Benchmarking — Information from PCS Teams SharePoint Documents

| Instrument | Telescope | Polarimetry Type | Wavelength Range | Spectral Resolution | Detector(s) | Pixel Scale | AO / Coronagraphy | Key Technical Details | Unknown Parameters |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PCS | Extremely Large Telescope | Planned imaging + spectropolarimetry | ~700–900 nm (baseline); visible + NIR planned | R~50 to >100,000 (mode dependent) | CCD44-8; SAPHIRA WFS; future VIS/NIR detectors | ~4.5 mas Airy at 850 nm | Extreme AO + coronagraphs | XAO contrasts ~1×10⁻⁶; throughput ~7.5%; Strehl ~50–60% at 750 nm; planned IFU + HDS + imaging + polarimetry modes | Final detector architecture; final pixel scale; final dark current; final polarimetric modulation scheme |
| SPHERE | Very Large Telescope | Imaging polarimetry | Visible + NIR (0.5–2.32 µm) | IFS: R~30–50; IRDIS LSS: R~50–350 | Hawaii II RG 2048×1024; ZIMPOL visible CCDs | IRDIS: 12.25 mas/pixel; IFS: 7.46 mas/pixel | SAXO XAO + coronagraphs | 41×41 actuator DM; >1 kHz AO; contrasts ~10⁻⁴ at few λ/D; IRDIS DPI + ZIMPOL DPI modes | Exact ZIMPOL dark current; full detector QE curves |
| IRDIS | SPHERE/VLT | Dual-polarization imaging (DPI) | 0.95–2.32 µm | Imaging; LSS R~50 or R~350 | Hawaii II RG | 12.25 mas/pixel | Coronagraphic compatible | Dual-band imaging and infrared polarimetry; 11″×11″ FoV | Detector dark current |
| ZIMPOL | SPHERE/VLT | High-contrast visible polarimetry | Visible (~500–900 nm) | Imaging polarimetry | Fast-demodulating CCDs | <30 mas angular resolution | Extreme AO + coronagraphs | Differential polarimetric imaging; polarimetric contrast <0.1%; calibrated beam-shift corrections | Exact read noise in operational mode |
| GPI | Gemini South | Dual-channel IFU polarimetry | 0.9–2.4 µm | R~30–80 | Teledyne HAWAII-2RG 2048×2048 | 14 mas/lenslet | Extreme AO + coronagraph | Contrast ~10⁻⁶ at 0.2–1″; dual-channel integral-field polarimeter; satellite spot calibration | Exact operational dark current |
| CRIRES+ | VLT | High-resolution spectropolarimetry | NIR | Up to R~100,000 | NIR detector arrays | High-res slit spectrograph | AO-assisted | High-resolution infrared spectroscopy + polarimetric capability | Exact polarimetric sensitivity |
| FORS2 | VLT | Imaging + spectropolarimetry | Visible | Low/medium resolution | CCD | Seeing-limited | None | Widely used optical polarimeter | Detector parameters in all configurations |
| HARPS | ESO 3.6m | Spectropolarimetry | Visible | R~115,000 | CCD | Fiber-fed echelle | None | Precision radial velocity + polarimetry modes | Detector dark current |
| SOFI | NTT | Infrared polarimetry | NIR | Low/medium | IR array | Seeing-limited | None | NIR imaging/spectroscopy with polarimetric mode | Detailed detector noise |
| EFOSC2 | NTT | Optical polarimetry | Visible | Low/medium | CCD | Seeing-limited | None | Imaging and spectropolarimetry | Full detector QE |

Note: This table reflects information as collated from the PCS Teams SharePoint repository. Some entries for PCS represent current planning estimates and may not reflect the final instrument design.

Table 5: Instrument Benchmarking — Extended Comparison (Including Literature and Public Documentation)

| Instrument | Category | Telescope | Polarimetry | Wavelength Range | Spectral Resolution | Detector | Dark Current | Read Noise | Pixel Scale | AO / Coronagraph | Reference |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PCS | High-contrast exoplanet polarimeter | ELT | Planned imaging + spectropolarimetry | 0.7–2.5 µm | R~50 to >100,000 | CCD44-8; SAPHIRA; future VIS/NIR | 3×10⁻⁶ e⁻/pix/s (CCD44-8) | 2.5 e⁻ rms | ~4.5 mas Airy at 850 nm | XAO + coronagraph | PCS roadmap + sensitivity documents |
| SPHERE | High-contrast exoplanet polarimeter | VLT | Imaging polarimetry | 0.5–2.32 µm | R~30–350 | Hawaii II RG + ZIMPOL CCDs | TBD | Mode dependent | 12.25 mas/pixel (IRDIS) | SAXO XAO + coronagraphs | ESO SPHERE documentation |
| IRDIS | Imaging polarimeter | VLT/SPHERE | Dual-polarization imaging | 0.95–2.32 µm | Imaging; LSS R~50/350 | Hawaii II RG 2048×1024 | TBD | TBD | 12.25 mas/pixel | XAO + coronagraph | ESO IRDIS documentation |
| ZIMPOL | Imaging polarimeter | VLT/SPHERE | Differential polarimetric imaging | 500–900 nm | Imaging | Fast modulation CCDs | TBD | Low-noise modes available | 7 mas/pixel | XAO + coronagraph | ESO ZIMPOL documentation |
| GPI | IFU polarimeter | Gemini South | Dual-channel polarimetry | 0.9–2.4 µm | R~30–80 | Teledyne HAWAII-2RG | TBD | TBD | 14 mas/lenslet | XAO + coronagraph | GPI calibration papers |
| SCExAO | High-contrast exoplanet polarimeter | Subaru | Polarimetric imaging modules | Visible + NIR | Depends on module | Various | TBD | TBD | Diffraction-limited | XAO + coronagraph | NAOJ SCExAO documentation |
| CHARIS | IFU polarimeter | Subaru/SCExAO | Spectropolarimetric imaging | JHK bands | R~75 (broadband) | NIR detector | TBD | TBD | 16.2 mas/lenslet | SCExAO | CHARIS-PDI papers |
| HiCIAO | Imaging polarimeter | Subaru | Polarimetric differential imaging | 0.9–2.5 µm | Imaging | HAWAII-2RG | TBD | TBD | 9.5 mas/pixel | AO188 + coronagraph | HiCIAO instrument papers |
| VAMPIRES | Imaging polarimeter | Subaru/SCExAO | Visible aperture masking polarimetry | Visible | Imaging | EMCCD | TBD | Low-noise EMCCD | Diffraction-limited | SCExAO | SCExAO/VAMPIRES documentation |
| Roman CGI | High-contrast exoplanet polarimeter | Nancy Grace Roman Space Telescope | Debris disk polarimetry | Visible | Imaging + spectroscopy | EMCCD | Ultra-low (space) | Very low | Space diffraction-limited | Space coronagraph | NASA Roman CGI documentation |
| POLLUX | Spectropolarimeter | LUVOIR concept | UV spectropolarimetry | 90–400 nm | High resolution | UV optimised detectors | TBD | TBD | N/A (space) | None | POLLUX consortium |
| HARMONI | IFU polarimeter (concept) | ELT | Possible future polarimetric mode | Visible + NIR | R~3000–20,000 | VIS + IR detectors | TBD | TBD | Multiple IFU scales | AO-assisted | HARMONI concept studies |
| CRIRES+ | Spectropolarimeter | VLT | High-resolution spectropolarimetry | NIR | R~100,000 | IR arrays | TBD | TBD | Slit spectrograph | AO-assisted | ESO CRIRES+ documentation |
| FORS2 | Spectropolarimeter | VLT | Imaging + spectropolarimetry | Visible | Low/medium | CCD | TBD | TBD | Seeing-limited | None | ESO FORS2 documentation |

Note: Entries marked ‘TBD’ reflect gaps to be filled during the benchmarking phase (WP 3.4.1). This table incorporates additional information beyond the PCS Teams SharePoint.

# 7.3  Instrument Trade Study: What Worked, What Didn’t Work, and Lessons for PCS

The table below synthesises the key lessons from seven existing high-contrast polarimetric instruments. For each instrument we identify: (1) techniques and capabilities that proved successful; (2) problems and limitations encountered; and (3) design lessons most applicable to the ELT/PCS polarimetry sub-system. Primary sources: van Holstein et al. (2020, 2021, 2023), Schmid et al. (2018), Anche et al. (2023), and supervisor notes (PCS Updated.docx).

| Instrument | System / Platform | What Worked | Problems & Challenges | Lessons for PCS Design |
| --- | --- | --- | --- | --- |
| SPHERE (General) | VLT / ESO (NIR + Visible) | • PDI (Qphi imaging) now the gold standard for protoplanetary disk imaging • Revealed unprecedented disk structure in AB Aur, HD 169142, and >100 systems • Uphi diagnostic standard: signal ~0 in well-calibrated data; non-zero Uphi indicates cross-talk • Coronagraphy + PDI combination achieves 10⁻³–1 0⁻⁴ contrast in Qphi • Qphi/Uphi technique is self-calibrating for many systematic errors | • Nasmyth platform: Al-coated VLT M3 introduces 1.5–3.5% telescope polarization (wavelength dependent) • Calibration overheads are large (~1 hr per target including standard stars) • Only bright stars accessible (R < 11 for ExAO performance) • Residual IP after calibration still ~0.5% (limits inner-working-angle sensitivity) | • PDI is THE technique for disk science; include from day one in PCS design • IP from Nasmyth fold mirrors is unavoidable; mitigate by placing HWP before the fold • Build complete Mueller matrix model of ELT + PCS optical path before first light • Uphi images must be reported in all publications as quality metric |
| SPHERE/ IRDIS | VLT / ESO NIR dual-beam (J, H, K bands) | • First full Mueller matrix calibration of an AO instrument (UT+M4+SPHERE+IRDIS) • IRDAP pipeline publicly available and validated on hundreds of datasets • Absolute polarimetric accuracy achieved: <0.1%; relative accuracy: <1% • HWP cycling + dual-beam removes first-order IP; derotator modelled per exposure • First detection of circumsubstellar disks around DH Tau B and GSC 6214-210 B • Wollaston prism in pupil plane: clean beam separation with no chromatic deviation | • H-band HWP retardance error: minimum polarimetric efficiency only 5% in H, 7% in K_s • Derotator (K-mirror type) introduces ¦m34¦ > 0.5 linear↔circular crosstalk; must be tracked for every angle • PSF beam shifts (Goos-Hänchen + Imbert-Federov) from inclined mirrors create polarization structure in PSF • Beam-shift-induced ghost PSFs limit contrast gain from PDI to factor ~350 in PSF core • No simultaneous multi-band polarimetry (one band at a time) • Derotator at 45°: destroys polarimetric efficiency entirely | • HWP retardance must be uniform and close to 180° across all science bands; specification critical • Derotator is the worst enemy of polarimetry; minimise optical complexity; model every rotation state • PSF beam shifts will be much larger for ELT F/0.9 vs SPHERE F/4 (effect scales as 1/f-number) • Beam-shift correction algorithms must be built into the PCS data pipeline from day one • IRDAP-style public calibration pipeline is essential for community science • If K-mirror derotator used in PCS, keep it away from 45° and optimise coatings to minimise retardance |
| SPHERE/ ZIMPOL | VLT / ESO Visible fast-mod. (500–900 nm) | • kHz EMCCD modulation: I⊥ and I∥ measured on same pixels → removes all atmospheric/speckle temporal variation • Polarimetric fidelity maintained over >3000:1 intensity dynamic range (clean Q/U images) • Highest spatial resolution optical polarimetry at 8m: 3.6 mas pixels, PSF 20–22 mas • Multiple coronagraph options (CLC, 4QPM) simultaneously available • Detects circumstellar polarized flux at contrast Cpol > 10⁻⁴ within 0.2 arcsec • Field/polarization angle offsets allow disentangling instrumental from sky signals | • VLT M3 Nasmyth mirror (Al-coated): ~4% IP in ZIMPOL 500–900 nm range • Derotator (3-mirror system): IP ~3%, wavelength-dependent crosstalk ¦m34¦ > 0.5 • No pupil-stabilised polarimetry → cannot combine PDI + ADI (Angular Differential Imaging) • Visible only: no NIR capability; unsuitable for young hot planets in thermal emission • Blocking filter inadequate outside 500–900 nm band • EMCCD detector pixel faults from charge-shifting require additional calibration steps • ~15% throughput penalty from polarimetric optics | • Fast modulation eliminates residual speckle noise in differential images – very powerful principle • However, kHz FLC modulation is NOT necessary: supervisor notes confirm HWP rotation at ~2 Hz achieves comparable results with less complexity • PCS must cover NIR (not just visible) for young planet thermal emission; IRDIS-style NIR channel is essential • Two-beam same-pixel design is the architectural ideal for polarimetric differential imaging • ELT Nasmyth IP from M4 + M5 will be the dominant systematic; HWP upstream of these mirrors is the fix |
| GPI | Gemini South NIR IFS + PDI (J, H, K_s) | • Lenslet IFS + Wollaston prism = simultaneous spectropolarimetry in J/H/K_s bands • Cassegrain mount (not Nasmyth) → no fold-mirror IP – greatly simplifies IP calibration • GPIES survey: >500 stars imaged; disks and companions detected in polarimetry mode • GPI-DRP pipeline publicly available and used by community • Wollaston prism in pupil plane gives high polarization purity • Detected scattered light in AB Aur disk, beta Pic disk, and protoplanetary systems | • Lenslet IFS sampling limits effective spatial resolution vs. dedicated imager (~49 mas lenslets vs. diffraction limit) • ~20% throughput loss from IFS optics (lenslet array, prisms, relay optics) • Spectral smearing in IFS reduces polarimetric precision in individual spectral channels • Complex IP calibration through many optical surfaces • No visible wavelength (< 900 nm) capability • High speckle noise at inner-working-angle limits performance for very close separations | • Cassegrain position dramatically simplifies IP calibration vs. Nasmyth; ELT PCS at Nasmyth must compensate via upstream HWP • IFS spectropolarimetry (GPI model) is very valuable for companion atmospheric characterisation • Wollaston prism in pupil plane validated as preferred NIR beam-splitting approach for PCS • Public pipeline from day one is essential for community uptake (lesson from GPI-DRP) • Dedicated polarimetric channel is better than IFS alone for disk imaging (spatial resolution critical) |
| SCExAO | Subaru / NAOJ ExAO platform (hosts CHARIS, VAMPIRES, MEC) | • Modular platform enables rapid upgrades and new instrument modules (CHARIS, VAMPIRES, MEC) • Best Strehl performance on 8m telescope in NIR (>90% H-band in good conditions) • LLOWFS (Lyot Low-Order Wavefront Sensor) demonstrated for post-coronagraphic wavefront control • Speckle nulling and electric field conjugation validated in on-sky tests • PDI with VAMPIRES module demonstrated successfully on stellar winds and disks • MKID-based fast photon-counting detectors (MEC camera) commissioned | • Nasmyth platform at Subaru: silver-mirror IP ~2–3% in NIR; must be calibrated • Multiple instruments sharing common beam → alignment compromises, calibration complexity, throughput losses • Complexity of many subsystems creates overlapping calibration requirements • AO performance degrades rapidly with guide star magnitude (R > 11 significant Strehl drop) | • Modular, upgradeable instrument design is valuable for long-lived instruments – PCS should plan upgrade paths • Dedicated LLOWFS for coronagraph stabilisation is critical at ELT scale where even small misalignments matter • Speckle nulling at ELT will need more DM actuators; PCS should plan for advanced wavefront sensing/control • IP from Nasmyth optics is unavoidable; HWP before M5 (or earliest accessible mirror position) is essential for PCS |
| CHARIS | Subaru / SCExAO NIR lenslet IFS (1.1–2.4 μm) | • Simultaneous J/H/K band coverage (1.1–2.4 μm) in broadband or narrowband modes • Spectral resolution R~18 (broadband) to R~70 (narrowband) → spectral characterisation of companions • Coupled to SCExAO coronagraph: enables coherent differentiation of planet vs. speckles • Detected and characterised multiple young directly-imaged planets (HR 8799, etc.) • Spectropolarimetry mode with Wollaston prism demonstrated in on-sky observations | • No dedicated fast-modulation polarimetry → atmospheric speckles change between polarisation states • Lenslet grid creates fixed-pattern noise that can mimic polarisation signals • Complex cross-channel calibration for polarimetry across 1.1–2.4 μm • Throughput penalty from lenslet + prism optics (~20–30%) • Very limited field of view (1.1″ × 1.4″) | • Dedicated polarimetry channel (not IFS alone) is preferred for disk imaging where spatial resolution is critical • Spectropolarimetry (CHARIS-style) is ideal for companion characterisation; PCS should include this as secondary mode • PCS design should consider: dedicated polarimetric imager for disk science + IFS capability for companion spectra • CHARIS validates the combination of coronagraph + IFS; IFS for PCS NIR channel is scientifically attractive |
| VAMPIRES | Subaru / SCExAO Visible dual-beam (600–800 nm) | • Two-camera simultaneous measurement of I⊥ and I∥ eliminates atmospheric differential noise completely • FLC fast modulation (~100 Hz effective) suppresses speckle variations • Demonstrated on AGB stars, stellar winds, protoplanetary disks at visible wavelengths • Polarisation contrast ratio > 1000:1 achieved routinely • Aperture masking mode provides interferometric spatial resolution • Recently upgraded with MKID-adjacent EMCCDs for improved sensitivity | • FLC (Ferroelectric Liquid Crystal) modulator: temperature sensitivity, long-term drift, ongoing calibration maintenance • FLC has chromatic retardance → complex wavelength-dependent Mueller matrix calibration needed • Nasmyth IP from Subaru + silver mirror: ~2–3% in visible • Combining FLC modulation with derotator rotation creates complex time-varying Mueller matrix • FLC modulation frequency must be synchronised precisely with EMCCD readout timing • Limited to visible wavelengths; no NIR capability | • Two-camera (simultaneous dual-beam) design is the single most important architectural choice for polarimetry: eliminates temporal noise • FLC modulation is powerful but maintenance-heavy and complex: supervisor strongly recommends HWP rotation at ~2 Hz for PCS for long-term operational reliability • Visible polarimetry (600–900 nm) is scientifically important for rocky planet reflected light detection at PCS • HWP modulation is more achromatic than FLC → better suited for the broad wavelength range of PCS • The "no flat-field uncertainty" advantage of dual-beam same-pixel designs must be central to PCS architecture |

8. Proposed PCS Polarimetric Capabilities

Based on the current state of the PCS design and the science case, the following polarimetric capabilities are proposed for PCS.

8.1 Wavelength Coverage

- Visible: approximately 0.6–1.0 µm, optimised for reflected-light exoplanet detection and polarimetry.

- Near-Infrared: approximately 1.0–2.5 µm for thermal emission and molecular spectroscopy.

8.2 Detector and Instrument Goals

- Low-noise visible and infrared detectors.

- Fast modulation capability for polarimetric differential imaging.

- High detector stability to maintain polarimetric calibration.

- Efficient throughput to IFU and high-dispersion spectroscopy (HDS) channels.

8.3 Flexible Observing Modes

- Direct imaging.

- Coronagraphic imaging.

- Imaging polarimetry.

- Integral field unit (IFU) spectroscopy.

- High-dispersion spectroscopy (HDS).

- Spectropolarimetry (low and high spectral resolution).

8.4 Complementarity with Other ELT Instruments

PCS should focus on capabilities uniquely enabled by extreme contrast, precision polarimetry, and high spatial resolution for reflected-light exoplanet science. Other ELT instruments complement PCS in broader-capability areas:

- HARMONI: general-purpose IFU spectroscopy.

- METIS: thermal infrared observations.

- ANDES: ultra-high-resolution spectroscopy.

PCS should therefore specialise in the high-contrast polarimetric niche rather than duplicating general instrument functionality.

9. Long-Term Vision

PCS should become:

- The flagship ELT instrument for reflected-light exoplanet characterisation.

- A pathfinder for future habitable planet imaging missions.

- A bridge between high-contrast imaging, spectroscopy, and precision polarimetry on extremely large telescopes.

10. Communications and Resources

10.1 Communications

Microsoft Teams (ESO PCS SharePoint site) will be used for both communication and document sharing. Email will be used for written communication and MS Teams for audio and video calls. After the initial kick-off meeting, regular monthly meetings will be established once the top-level requirements are defined. A mailing list may also be set up.

10.2 Software Resources

Design and modelling tools:

- Polarisation ray tracing: Zemax OpticStudio.

- Simulation and data analysis: Python, IDL.

General utility tools:

- Microsoft Word, Microsoft Excel, Microsoft Visio (or equivalent drawing software).

10.3 Documentation

- ESO PCS WP3 SharePoint repository.

# 11.  Outstanding Actions — Team Input Required

ACTION (Daniel Smith — Polarimetry Lead):

A draft SPIE conference poster (PCS_Polarimetry_SPIE_Poster.pptx) has been prepared. It explains the fundamental difference between PDI as a contrast technique and polarimetry as physical characterisation, and introduces the ELT/PCS polarimetry study. Placeholder figure boxes are included for figures from the Leiden University papers. Before submitting to SPIE, the following input is required from the polarimetry team:

•  CONFIRMED — Poster title: "Lessons Learnt from Existing Instruments and R&D Programs for the Implementation of the Polarimetric Mode of the ELT’s High-Contrast Imager PCS"

•  CONFIRMED — Authors: D. Smith (Leiden),  S. Y. Haffert (Leiden), S. Maharana (Oxford),  M. Tecza (Oxford),  M. Lucas (Arizona), M. Langlois (Lyon),  F. Snik (Leiden)

•  Selection of actual figures from Leiden papers (van Holstein 2020, Schmid 2018, Ginski 2023, Stam 2004) to replace placeholder boxes

•  Technical review of poster content for accuracy, completeness, and appropriate detail level for a conference audience

•  SPIE acknowledgements, funding statements, and grant numbers as required

•  Agreement on whether beam-splitting architecture options should feature in the poster or be reserved for oral presentation

•  Any additional science cases or open questions to highlight for the SPIE community

Target: SPIE Astronomical Telescopes and Instrumentation 2026 [submission deadline TBC].